## Pivots (hidden)
Row Labels | Sum of Total Efforts | % Allocation
A5 | 7266 | 22.9%
B1 | 7549.5 | 23.8%
B2 | 8095.5 | 25.52%
C1 | 2635.5 | 8.307%
C2 | 4226.25 | 13.32%
D1 | 420 | 1.324%
D2 | 850.5 | 2.681%
E1 | 682.5 | 2.151%
Grand Total | 31725.75 | 100%
Row Labels | Sum of Total
India | 89.79%
US | 10.21%
Grand Total | 100%

## Estimator 4 RL (hidden)
[6 empty] | 5.75 | 24 | 43.5 | 68.5 | 84 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 86 | 86 | 84 | 83 | 81 | 76 | 66 | 27 | 1510.75 | 31725.75
[6 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
BU | Team | Role | Local Grade | Global Grade | Shore | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | Total Months | Total Efforts
NA I&D | Governance | Engagement Lead | D | D2 | US | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 20.5 | 430.5
GCP | Governance | Offshore Delivery Lead | E | E1 | India | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 20.5 | 430.5
NA I&D | Architecture | Data Architect | C | C2 | US | [21 empty] | 20 | 420 | bar: May to Jan
GCP | Architecture | Solution Architect | D | D2 | India | [21 empty] | 20 | 420 | bar: May to Jan
NA I&D | Architecture | Platform/Cloud Architect | C | C2 | US | May: 0.75; Jun: 1; Jul: 1; Aug: 1 | 3.75 | 78.75
GCP | Architecture | Platform/Cloud Architect | D | D1 | India | [21 empty] | 20 | 420 | bar: May to Jan
Testing | Quality Assurance | QA Lead | C | C2 | US | [21 empty] | 19 | 399 | bar: May to Jan
NA I&D | Requrements | Lead Analyst | C | C1 | US | [21 empty] | 19 | 399 | bar: May to Jan
NA I&D | Requrements | Data Analyst 1 | B | B2 | US | [21 empty] | 20 | 420 | bar: May to Jan
GCP | Requrements | Data Analyst 2 | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
GCP | Requrements | Data Analyst 3 | B | B1 | India | [21 empty] | 20 | 420 | bar: May to Jan
GCP | Platform & DevOps | DevOps SME | C | C1 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 18.5 | 388.5
IDEA | Platform & DevOps | IDEA SME | E | E1 | India | [21 empty] | 12 | 252 | bar: May to Jan
IDEA | Platform & DevOps | IDEA SME | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
NA I&D | Reverse Engineering | ETL SME (Inf + TD) | B | B2 | US | [21 empty] | 16 | 336 | bar: May to Jan
EDE | Reverse Engineering | Teradata SME | C | C2 | India | [21 empty] | 19 | 399 | bar: May to Jan
EDE | Reverse Engineering | Informatica SME | C | C1 | India | [21 empty] | 16 | 336 | bar: May to Jan
EDE | Reverse Engineering | Informatica SME | B | B1 | India | [21 empty] | 19 | 399 | bar: May to Jan
GCP | Schema Migration | Schema Migration Lead | C | C2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 17.5 | 367.5
GCP | Schema Migration | Developer (GCP) | B | B2 | India | [21 empty] | 18 | 378 | bar: May to Jan
GCP | Schema Migration | Developer (GCP) | A | A5 | India |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 17.5 | 367.5
GCP | Data Migration 1 | Data Migration Lead | C | C2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 18.5 | 388.5
NA I&D | Data Migration 1 | Developer (GCP) | B | B2 | US |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 18.5 | 388.5
GCP | Data Migration 1 | Developer (GCP)/ Tester | B | B1 | India |  | 0.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 36 | 756
GCP | Data Migration 1 | Developer (GCP) | A | A5 | India |  | 0.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 36 | 756
GCP | Data Migration 2 | Data Migration Lead | C | C1 | India |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 17.5 | 367.5
NA I&D | Data Migration 2 | Developer (GCP) | B | B2 | US |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 17.5 | 367.5
GCP | Data Migration 2 | Developer (GCP)/ Tester | B | B1 | India |  |  | 0.5 | 1.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 50 | 1050
GCP | Data Migration 2 | Developer (GCP) | A | A5 | India |  |  | 0.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 35 | 735
GCP | Data Ingestion 1 | Data Ingestion Lead | C | C2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 17.5 | 367.5
GCP | Data Ingestion 1 | Developer (GCP) | B | B2 | India |  | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 37.5 | 787.5
GCP | Data Ingestion 1 | Developer (GCP)/ Tester | B | B1 | India |  | 0.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 36 | 756
GCP | Data Ingestion 1 | Developer (GCP)/ Tester | A | A5 | India |  | 0.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 32 | 672
GCP | Data Ingestion 2 | Data Ingestion Lead | C | C2 | India | [21 empty] | 16 | 336 | bar: May to Jan
GCP | Data Ingestion 2 | Developer (GCP) | B | B2 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 29 | 609
GCP | Data Ingestion 2 | Developer (GCP)/ Tester | B | B1 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 31 | 651
GCP | Data Ingestion 2 | Developer (GCP)/ Tester | A | A5 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 29 | 609
GCP | Data Distillation 1 | Data Distillation Lead | C | C2 | India | [21 empty] | 18 | 378 | bar: May to Jan
GCP | Data Distillation 1 | Developer (GCP) | C | C1 | India | [21 empty] | 0 | 0
GCP | Data Distillation 1 | Developer (GCP) | B | B2 | India |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 36 | 756
GCP | Data Distillation 1 | Developer (GCP)/ Tester | B | B1 | India |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 36 | 756
GCP | Data Distillation 1 | Developer (GCP)/ Tester | A | A5 | India |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 36 | 756
GCP | Data Distillation 2 | Data Distillation Lead | C | C2 | India | [21 empty] | 17 | 357 | bar: May to Jan
GCP | Data Distillation 2 | Developer (GCP) | C | C1 | India | [21 empty] | 0 | 0
GCP | Data Distillation 2 | Developer (GCP) | B | B2 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 34 | 714
GCP | Data Distillation 2 | Developer (GCP)/ Tester | B | B1 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 34 | 714
GCP | Data Distillation 2 | Developer (GCP)/ Tester | A | A5 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 34 | 714
GCP | Data Distillation 3 | Data Distillation Lead | C | C2 | India | [21 empty] | 16 | 336 | bar: May to Jan
GCP | Data Distillation 3 | Developer (GCP) | C | C1 | India | [21 empty] | 0 | 0
GCP | Data Distillation 3 | Developer (GCP) | B | B2 | India |  |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 32 | 672
GCP | Data Distillation 3 | Developer (GCP)/ Tester | B | B1 | India |  |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 32 | 672
GCP | Data Distillation 3 | Developer (GCP)/ Tester | A | A5 | India |  |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 32 | 672
DCX | UI Development | UI Developer/ Angular | B | B2 | India | Aug: 0.5; Sep: 1; Oct: 0.5 | 2 | 42
DCX | UI Development | UI Developer/ Angular | B | B2 | India | Aug: 0.5; Sep: 1; Oct: 0.5 | 2 | 42
AI&A | Governance | Offshore Reporting Lead | C | C2 | India | [21 empty] | 19 | 399 | bar: May to Jan
AI&A | Report Repoint (Q/T) | Report Developer | B | B2 | India |  |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17.5 | 367.5
AI&A | Report Repoint (SAP) | Report Developer | C | C1 | India | [21 empty] | 18 | 378 | bar: May to Jan
AI&A | Report Repoint (SAP) | Report Developer | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
AI&A | Report Repoint (SAP) | Report Developer / Tester | B | B1 | India |  |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17.5 | 367.5
AI&A | Report Repoint (SAP) | Report Developer / Tester | A | A5 | India |  |  |  | 0.5 | 1 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 31 | 651
AI&A | Report Repoint (Tibco) | Report Developer | C | C1 | India |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 17.5 | 367.5
AI&A | Report Repoint (Tibco) | Report Developer | B | B2 | India |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18.5 | 388.5
AI&A | Report Repoint (Tibco) | Report Developer / Tester | B | B1 | India | [21 empty] | 18 | 378 | bar: May to Jan
AI&A | Report Repoint (Tibco) | Report Developer / Tester | A | A5 | India |  |  |  | 1 | 1 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 31.5 | 661.5
Testing | Quality Assurance | Test Lead | C | C1 | India | [21 empty] | 19 | 399 | 2730 | bar: May to Jan
Testing | Quality Assurance | Sr Testers | B | B2 | India |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 |  | 30 | 630
Testing | Quality Assurance | Tester | B | B1 | India |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 |  | 30 | 630
Testing | Quality Assurance | Jr Tesers | A | A5 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  | 32 | 672
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0

## Summary
DE | 2697
DS-Predictive | 450
Reporting | 500
| 3647 | 21.4529

## Data Engineering Efforts
Phase | Efforts | % Add On | Comments
Project Management | 215.744 | 8% |  | #FTEs 12 Mnths | 11.2367
Analysis and Requirement Gathering | 269.68 | 10% | DCX team will do data mapping & transfomration specifications
Design Efforts | 323.616 | 12%
Development and Unit Testing | 1348.4 | 50%
System(& Integration) Testing | 323.616 | 12%
UAT | 134.84 | 5%
Deployment & Hypercare | 80.904 | 3%
Total Efforts in PDs | 2696.8 |  |  | 11.2375
[5 empty] | Complexity Distribution |  |  | Cut Estimates to Build & Test in PDs |  |  | Total Efforts in PDs | % Savings (Reusability/ Tools/ Automations) | PD post Savings | Comments
BU | SL | Object Type | # Objects/ Jobs | Method of Implementation | Simple | Mid | Complex | Simple | Mid | Complex |  |  |  |  | Avg
I&D | Azure | Data Ingestion Jobs - Batch | 56 | ADB/ADF Jobs for Daata Ingestion incremental Batch | 30% | 40% | 30% | 1 | 2 | 3 | 112 | 40% | 67.2 | Using IDEA Data Ingestion /Azure MX metadata driven approach + Same used for 1st history load | 1.2
DCX | DCX | Data Ingestion Jobs - APIs | 168 | Mulesoft data ingestion jobs using APIs from Souce to RAW (ADLS ) Incremental | 30% | 40% | 30% | 1.5 | 2 | 3.5 | 386.4 | 20% | 309.12 | Parameterizing re-usable jobs & repeating sources + Same used for 1st history load | 1.84
I&D | Azure | Data Ingestion Jobs - Streaming | 56 | Kafka/Confluence Streaming Jobs | 30% | 40% | 30% | 2 | 3 | 4 | 168 | 40% | 100.8 | Using IDEA Data Ingestion /Azure MX metadata driven approach + Same used for 1st history load | 1.8
I&D | Azure | Data Curation/Transformation Jobs - ADF/ADB | 196 | Get quality /enriched data from Profisee & Transorm/curate into Azure Delta Lake using ADF/ADB | 30% | 40% | 30% | 2 | 2.5 | 3 | 490 | 40% | 294 | Using IDEA Data Ingestion /Azure MX metadata driven approach | 1.5
I&D | Azure | Curated/Transformed Jobs to Consuption Layer | 78 | Get curated/transformed data into Consuption/Sementic layer using ADF/ADF in Synapse | 30% | 40% | 30% | 2 | 4 | 6 | 312 | 40% | 187.2 | Using IDEA Data Ingestion /Azure MX metadata driven approach | 2.4
I&D | Azure | ADB/ADF jobs for Downsteam systems | 8 | Get consuption data & send it to downsteam systems using ADF/ADB Batch | 30% | 40% | 30% | 1.5 | 2 | 3 | 17.2 | 40% | 10.32 | Using IDEA Data Ingestion /Azure MX metadata driven approach | 1.29
I&D | Azure | Data Masking Jobs | 56 | Using ADF/ADB for persistant / Azure Dynamic data masking for PII/PCI data | 30% | 40% | 30% | 1 | 2.5 | 4 | 140 | 0% | 140 |  | 2.5
I&D | Azure | Job Sheduling efforts 20% of total Jobs | 123.6 | Job sheduling in Airflow/ADF - 20% of total jobs | 30% | 40% | 30% | 0.5 | 1 | 1.5 | 123.6 | 0% | 123.6 |  | 1
I&D | Azure | Ci/CD pipelines for Dev-Ops/Infra | 1 | CI-CD dev-ops pipelines (Git/Maven/Jenkins/Arti factory(Nexus)) | 0% | 100% | 0% | 0 | 30 | 0 | 30 | 30% | 21 | IDEA Dev-Ops CI-CD FM | 21
I&D | Azure | ABCR FM Customization | 1 | ABCR FM Customization | 0% | 100% | 0% | 0 | 16 | 0 | 16 | 50% | 8 | IDEA ABCR FM | 8
I&D | Azure | Azure AD Sync up for athentication & Athorization | 1 | Azure AD Sync up for athentication & Athorization | 0% | 100% | 0% | 0 | 10 | 0 | 10 | 0% | 10
DCX | DCX | CI/CD for Mulesoft/Infra | 1 | Mulesoft CI/CD Setup (Git/Maven/Jenkins/Arti factory(Nexus)) - Customization efforts | 0% | 100% | 0% | 0 | 150 | 0 | 15 | 0% | 15
I&D | Azure | Moving from Landing to Raw Zone | 224 | Format conversion jobs | 30% | 40% | 30% | 0.25 | 1 | 1.5 | 207.2 | 70% | 62.16 | Parameterized for similar file types to standerdize file types
[5 empty] | 30% | 40% | 30% | 1.5 | 2 | 3 | 0 | 0% | 0
[5 empty] | 30% | 40% | 30% | 1.5 | 2 | 3 | 0 | 0% | 0
[5 empty] | 30% | 40% | 30% | 1.5 | 2 | 3 | 0 | 0% | 0
[5 empty] | 30% | 40% | 30% | 1.5 | 2 | 3 | 0 | 0% | 0
[5 empty] | 30% | 40% | 30% | 1.5 | 2 | 3 | 0 | 0% | 0
[11 empty] | Without Savings | With Savings
[10 empty] | Man-days | 2027.4 | 1348.4
[11 empty] | % Savings | 33.49%

## Power BI Reports
SCM | 15
Warranty Ana | 5
Planning & FCST | 5

## Predictive-DS
Demand forecasting; Order‑to‑Ship / Order‑to‑Cash forecasting

## PP-RL Plan
|  |  | Due Deligence & Blue Print Phase | [7 empty] | Execution Phase
|  |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | M3 | M4 | M5 | M6 | M7 | M8 | M9
| DD & Blueprint Phase | Project Kick-Off | bar: Due Deligence & Blue Print Phase Wk1
Workshops | bar: Due Deligence & Blue Print Phase Wk2 to Due Deligence & Blue Print Phase Wk6
Use case priorotization | bar: Due Deligence & Blue Print Phase Wk3 to Due Deligence & Blue Print Phase Wk7
Platform Options | bar: Due Deligence & Blue Print Phase Wk2 to Due Deligence & Blue Print Phase Wk4
|  | Platform Foundation | Due Deligence & Blue Print Phase Wk3: Dev; Due Deligence & Blue Print Phase Wk8: QA; Execution Phase M4: Prod
Security & access | bar: Due Deligence & Blue Print Phase Wk5 to Due Deligence & Blue Print Phase Wk6
[11 empty] | MVP 1 |  | MVP 2 |  | MVP 3
Shore | Grade | Roles | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | M3 | M4 | M5 | M6 | M7 | M8 | M9
| On | BI Arch | bar: Due Deligence & Blue Print Phase Wk1 to Execution Phase M9
| On | Data Modeller | bar: Due Deligence & Blue Print Phase Wk1 to Execution Phase M9
| On | BA | bar: Due Deligence & Blue Print Phase Wk1 to Execution Phase M9
| Off | Power BI | bar: Due Deligence & Blue Print Phase Wk1 to Execution Phase M9
| Off | xx
xx
xx
xx
xx

## Estimator (hidden)
Phase | Efforts | Comments
Project Management | 318.3075 | 7.5%
Analysis and Requirement Gathering | 275.8665 | 6.5% |  | ~FTEs | 18.8332
Design and Data Modeling | 509.2919 | 12%
Development and Unit Tesing | 4244.0994 | 4244.0994
System(& Integration) Testing | 403.1894 | 9.5%
UAT | 190.9845 | 4.5%
Deployment | 63.6615 | 1.5%
KT & Handoff | 21.2205 | 0.5%
Total Efforts | 6026.6212
[5 empty] | Complexity Matrix |  |  | Cut Estimates to Build & Test in Hrs |  |  | Total Efforts in PDs | % Savings | PD post Savings | Comments
BU | SL | Object Type | # Objects/ Jobs | Method of Migration | Simple | Mid | Complex | Simple | Mid | Complex
I&D | GCP | No. Of Tables / Files | 15724 | BigQuery Data Transfer APIs (Lift & Shift) | 30% | 40% | 30% | 0.5 | 0.75 | 1 | 1310.3333 | 50% | 655.1667 | Teradata to Big Query schema migration tool to achieve quick conversions BigQuery Data Transfer Service as migration agent for Teradata Compute migration tool for BTEQ to BQ conversion
I&D | GCP | # of Views, Semantic Layer | 25992 | BigQuery Data Transfer APIs (Lift & Shift) | 70% | 20% | 10% | 0.25 | 0.5 | 0.75 | 1010.8 | 50% | 505.4
I&D | Infa | # of ETL views with business Logic | 4052 | Informatica Same logic with minimal retro efforts (Lift & Shift, Reporint) | 100% | 0% | 0% | 3 | 4 | 5 | 1350.6667 | 50% | 675.3333 | No code change, only change connection , retrofication & smoke test
I&D | GCP | Informatica Transformation in GBQ SP | 2148 | BigQuery Data Transfer APIs (Lift & Shift) | 100% | 0% | 0% | 0.25 | 1 | 1.5 | 59.6667 |  | 59.6667 | Use schema /DB level approach for migration
I&D | GCP | Stored Procedure Migration from TD to Big Query | 1005 | BigQuery Data Transfer APIs (Lift & Shift) | 100% | 0% | 0% | 3 | 4 | 5 | 335 | 20% | 268 | Same logic, minimal retrofication and bug fixing if applicable , no requirements & same logic , lift & shift
I&D | Infa | # TD to Sources (Oracle) Write-back Jobs | 394 | Informatica Same logic with minimal retro efforts (Lift & Shift, Reporint) | 80% | 15% | 5% | 3 | 4 | 5 | 142.2778 | 20% | 113.8222 | Same logic, minimal retrofication and bug fixing if applicable , no requirements & same logic , lift & shift
I&D | GCP | # Cloud Storage buckets & archival Scripts | 50 | Same logic with minimal retrofication & change targets | 30% | 40% | 30% | 0.5 | 1 | 2 | 6.3889 |  | 6.3889 | No code change, only change connection , retrofication & smoke test
I&D | Spot | # of Reports reporting efforts (SPOT fire) | 2484 | Change Source Connections & Minimal retrofications with smoke test | 80% | 15% | 5% | 3 | 4 | 5 | 897 |  | 897 | No code change, only change connection & smoke test
I&D | BO | # of Reports reporting efforts (SAP BO) | 1039 | Smoke test only & minor bug fix if any | 80% | 15% | 5% | 3 | 4 | 5 | 375.1944 | 30% | 262.6361 | No code change, only change connection, smoke test & minor bug fix if any
I&D | BO | # of Universe Reports reporting efforts (SAP BO) | 89 | Change Source Connections & Minimal retrofications with smoke test(no major changes in the code , lift & shift) | 80% | 15% | 5% | 3 | 4 | 5 | 32.1389 | 30% | 22.4972 | Will be done at universe level, no major code changes, only retro & smoke test in scope, no reqirements
I&D | Qlik/Tab | # of Reports reporting efforts (Tableau) | 8 | ? | 30% | 40% | 30% |  |  |  | 0 | ?
I&D | Qlik/Tab | # of Reports reporting efforts (QlikView) | 32 | ? | 30% | 40% | 30% |  |  |  | 0 | ?
I&D | Qlik/Tab | # of Reports reporting efforts (Composite) | 1 | ? | 30% | 40% | 30% |  |  |  | 0 | ?
I&D | Qlik/Tab | # of Reports reporting efforts (P&T) | 3 | ? | 30% | 40% | 30% |  |  |  | 0 | ?
DCX | SF | API Integration Framework-Salesforce-Cast Iron | 230 | ? | 30% | 40% | 30% |  |  |  | 0 | ?
I&D | GCP | RDM UI Build, RDM Cloud SQL Server to GBQ automated data refresh | 2654 | Creation GCP Data Pipes with like to like funcationality | 30% | 40% | 30% | 2 | 3 | 4 | 884.6667 | 20% | 707.7333 | Mimic existing fucntionality with no requirements
I&D | GCP | Scheduling & Orchestration Scripts | 6039 | Mimic existing sheduler with Google Cloud Scheduler | 50% | 50% | 0% | 0.1 | 0.2 | 0.5 | 100.65 | 0.3 | 70.455 | No requirements only to re-use & mimic existing sheduler logic
[11 empty] | Without Savings | With Savings
[10 empty] | ~FTEs | 20.3274 | 13.2628
[11 empty] | % Savings | 53.27%

## Estimator 3 RL (hidden)
[6 empty] | 6.25 | 26 | 47.5 | 78 | 97 | 99 | 98 | 98 | 98 | 98 | 97 | 97 | 97 | 96 | 96 | 96 | 94 | 88 | 81 | 70 | 38 | 1695.75 | 35610.75
[6 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
BU | Team | Role | Local Grade | Global Grade | Shore | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | Total Months | Total Efforts
NA I&D | Governance | Engagement Lead | D | D2 | US | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 20.5 | 430.5
GCP | Governance | Offshore Delivery Lead | E | E1 | India | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 20.5 | 430.5
NA I&D | Architecture | Data Architect | C | C2 | US | [21 empty] | 20 | 420 | bar: May to Jan
GCP | Architecture | Solution Architect | D | D2 | India | [21 empty] | 21 | 441 | bar: May to Jan
NA I&D | Architecture | Platform/Cloud Architect | C | C2 | US | May: 0.75; Jun: 1; Jul: 1; Aug: 1 | 3.75 | 78.75
GCP | Architecture | Platform/Cloud Architect | D | D1 | India | [21 empty] | 20 | 420 | bar: May to Jan
Testing | Quality Assurance | QA Lead | C | C2 | US | [21 empty] | 19 | 399 | bar: May to Jan
NA I&D | Requrements | Lead Analyst | C | C1 | US | [21 empty] | 19 | 399 | bar: May to Jan
NA I&D | Requrements | Data Analyst 1 | B | B2 | US | [21 empty] | 20 | 420 | bar: May to Jan
GCP | Requrements | Data Analyst 2 | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
GCP | Requrements | Data Analyst 3 | B | B1 | India | [21 empty] | 20 | 420 | bar: May to Jan
GCP | Platform & DevOps | DevOps SME | C | C1 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 18.5 | 388.5
IDEA | Platform & DevOps | IDEA SME | E | E1 | India | [21 empty] | 12 | 252 | bar: May to Jan
IDEA | Platform & DevOps | IDEA SME | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
NA I&D | Reverse Engineering | ETL SME (Inf + TD) | C | C1 | US | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 16.5 | 346.5
EDE | Reverse Engineering | Teradata SME | C | C2 | India | [21 empty] | 19 | 399 | bar: May to Jan
EDE | Reverse Engineering | Informatica SME | C | C1 | India | [21 empty] | 16 | 336 | bar: May to Jan
EDE | Reverse Engineering | Informatica SME | B | B1 | India | [21 empty] | 19 | 399 | bar: May to Jan
GCP | Schema Migration | Schema Migration Lead | C | C2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 18.5 | 388.5
GCP | Schema Migration | Developer (GCP) | B | B2 | India | [21 empty] | 18 | 378 | bar: May to Jan
GCP | Schema Migration | Developer (GCP) | A | A5 | India |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 17.5 | 367.5
GCP | Data Migration 1 | Data Migration Lead | C | C2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19.5 | 409.5
NA I&D | Data Migration 1 | Developer (GCP) | B | B2 | US |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19.5 | 409.5
GCP | Data Migration 1 | Developer (GCP)/ Tester | B | B1 | India |  | 0.5 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 53.5 | 1123.5
GCP | Data Migration 1 | Developer (GCP) | A | A5 | India |  | 0.5 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 35.5 | 745.5
GCP | Data Migration 2 | Data Migration Lead | C | C1 | India |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18.5 | 388.5
NA I&D | Data Migration 2 | Developer (GCP) | B | B2 | US |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18.5 | 388.5
GCP | Data Migration 2 | Developer (GCP)/ Tester | B | B1 | India |  |  | 0.5 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 50.5 | 1060.5
GCP | Data Migration 2 | Developer (GCP) | A | A5 | India |  |  | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 34.5 | 724.5
GCP | Data Ingestion 1 | Data Ingestion Lead | C | C2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19.5 | 409.5
GCP | Data Ingestion 1 | Developer (GCP) | B | B2 | India |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 16.5 | 346.5
GCP | Data Ingestion 1 | Developer (GCP)/ Tester | B | B1 | India |  | 0.5 | 1.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 47 | 987
GCP | Data Ingestion 1 | Developer (GCP)/ Tester | A | A5 | India |  | 0.5 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  |  | 30.5 | 640.5
GCP | Data Ingestion 2 | Data Ingestion Lead | C | C2 | India | [21 empty] | 18 | 378 | bar: May to Jan
GCP | Data Ingestion 2 | Developer (GCP) | B | B2 | India | [21 empty] | 15 | 315 | bar: May to Jan
GCP | Data Ingestion 2 | Developer (GCP)/ Tester | B | B1 | India |  |  |  | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 43 | 903
GCP | Data Ingestion 2 | Developer (GCP)/ Tester | A | A5 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  |  | 28 | 588
GCP | Data Distillation 1 | Data Distillation Lead | C | C2 | India | [21 empty] | 19 | 399 | bar: May to Jan
GCP | Data Distillation 1 | Developer (GCP) | C | C1 | India | [21 empty] | 18 | 378 | bar: May to Jan
GCP | Data Distillation 1 | Developer (GCP) | B | B2 | India |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 36 | 756
GCP | Data Distillation 1 | Developer (GCP)/ Tester | B | B1 | India |  |  | 1.5 | 2.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 52 | 1092
GCP | Data Distillation 1 | Developer (GCP)/ Tester | A | A5 | India |  |  | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 50 | 1050
GCP | Data Distillation 2 | Data Distillation Lead | C | C2 | India | [21 empty] | 18 | 378 | bar: May to Jan
GCP | Data Distillation 2 | Developer (GCP) | C | C1 | India | [21 empty] | 17 | 357 | bar: May to Jan
GCP | Data Distillation 2 | Developer (GCP) | B | B2 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 34 | 714
GCP | Data Distillation 2 | Developer (GCP)/ Tester | B | B1 | India |  |  |  | 2.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 50.5 | 1060.5
GCP | Data Distillation 2 | Developer (GCP)/ Tester | A | A5 | India |  |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 49 | 1029
GCP | Data Distillation 2 | Data Distillation Lead | C | C2 | India | [21 empty] | 17 | 357 | bar: May to Jan
GCP | Data Distillation 3 | Developer (GCP) | C | C1 | India | [21 empty] | 16 | 336 | bar: May to Jan
GCP | Data Distillation 3 | Developer (GCP) | B | B2 | India |  |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 32 | 672
GCP | Data Distillation 3 | Developer (GCP)/ Tester | B | B1 | India |  |  |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 47 | 987
GCP | Data Distillation 3 | Developer (GCP)/ Tester | A | A5 | India |  |  |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 46 | 966
DCX | UI Development | UI Developer/ Angular | C | C1 | India | Aug: 1; Sep: 1; Oct: 0.5 | 2.5 | 52.5
DCX | UI Development | UI Developer/ Angular | B | B2 | India | Aug: 1; Sep: 1; Oct: 0.5 | 2.5 | 52.5
AI&A | Governance | Offshore Reporting Lead | C | C2 | India | [21 empty] | 20 | 420 | bar: May to Jan
AI&A | Report Repoint (Q/T) | Report Developer | C | C1 | India | [21 empty] | 17 | 357 | bar: May to Jan
AI&A | Report Repoint (SAP) | Report Developer | C | C1 | India | [21 empty] | 19 | 399 | bar: May to Jan
AI&A | Report Repoint (SAP) | Report Developer | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
AI&A | Report Repoint (SAP) | Report Developer / Tester | B | B1 | India | [21 empty] | 18 | 378 | bar: May to Jan
AI&A | Report Repoint (SAP) | Report Developer / Tester | A | A5 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 33 | 693
AI&A | Report Repoint (Tibco) | Report Developer | C | C1 | India | [21 empty] | 19 | 399 | bar: May to Jan
AI&A | Report Repoint (Tibco) | Report Developer | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
AI&A | Report Repoint (Tibco) | Report Developer / Tester | B | B1 | India |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 36 | 756
AI&A | Report Repoint (Tibco) | Report Developer / Tester | A | A5 | India |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 33 | 693
Testing | Quality Assurance | Test Lead | C | C1 | India | [21 empty] | 19 | 399 | 2715 | 2715 | bar: May to Jan
Testing | Quality Assurance | Sr Testers | B | B2 | India | [21 empty] | 19 | 399 | bar: May to Jan
Testing | Quality Assurance | Tester | B | B1 | India | [21 empty] | 19 | 399 | bar: May to Jan
Testing | Quality Assurance | Jr Tesers | A | A5 | India |  |  | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 |  | 55 | 1155
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0
[27 empty] | 0 | 0

## Assumptions (hidden)
# | Assumption
1 | No Data Modelling efforts required for Reporting side.
2 | Connection between Cast Iron and Teradata is via REST APIs only.
3 | Regarding "RDM Cloud SQL Server to GBQ automated data refresh" - Assuming 2654 tables needs to be refreshed by batch jobs. 4 tables per job. i.e. 663 jobs.
4 | JDK needs to install in the enviromrnt in tomcat server BO application server and BO client tool needs to install in the same server/system for METADATA EXTRACTOR
5 | BO 4.3 platform should be available before starting this project.
6 | Installation,configuration and user managment of SAP BO 4.3 server is out of scope.
7 | We assumed that only Teradata and GCP data sources will be in scope.
8 | If redesigning of webi reports are required then extra efforts will be included.
9

## SAP BO Complexity Definition (hidden)
GCP Artifacts Complexity Definition
Object Name | Simple | Medium | Complex
Table | less than 500 GB | Between 500 Gb & 5 TB | More than 5 TB
View | Referring to less than 3 tables | Referring to between 3 to 6 tables | Referring to more than 6 tables
Stored Procedure | Less than 30 lines of code | Between 30 lines to 100 lines of code | More than 100 lines of code
Data FLow job | less than 3 transformations | Between 3 to 7 transformations | More than 7 transformations
Composer | less than 5 tasks or steps | Between 5 to 9 tasks or steps | More than 9 tasks or steps
SAP BO
Universe Paramater | Simple | Medium | Complex
# of Tables/Joins | < 3 | 3 to 5 | 5 to 10 | # of Tables/Joins '5 to 10'
No Of Fields per table | <= 15 | > 15 <= 30 | 30 to 50 | No Of Fields per table '30 to 50 '
Avg. Data Size | <=1 M | >1 M <= 2M | >2M <= 10M | Avg. Data Size '>2M <= 10M '
Use of Views and Stored Procedures | N/A | N/A | <=5 | Use of Views and Stored Procedures '<=5'
Custom SQL Script | 1 | 1 to 2 | 3 to 5 | Custom SQL Script '3 to 5'
Number of Data Sources | 1 | <= 3 | 3 to 6 | Number of Data Sources '3 to 6'
Basic data conversion (Format, datetime conversion, currency, string operation etc…) | <=5 | 5 to 10 | 11 to 15 | Basic data conversion (Format, datetime conversion, currency, string operation etc…) '11 to 15 '
No of KPI's | <=2 | >2 and <=5 | 5 to 10 | No of KPI's '5 to 10'
No aggregated awareness/Index awareness | N/A | N/A | < 2 | No aggregated awareness/Index awareness '< 2'
#Prompts/runtime parameter | <=3 | >3 <= 5 | 6 to 10 | #Prompts/runtime parameter '6 to 10 '
Webi Report Parameter | Simple | Medium | Complex
# of Queries | < 2 | 2 to 4 | > 4
No of Objects per query | <= 10 | > 10 <= 20 | > 20
Avg. Data Size | <=1 M | >1 M <= 2M | >2M <= 10M
Use of Filters | < 4 | 4 to 10 | > 10
Custom SQL Script | N/A | N/A | <=3
Number of Data Sources | N/A | N/A | N/A
Webi Variables (Format, datetime conversion, currency, string operation etc…) | <=5 | 5 to 10 | 11 to 15
No of KPI's | <=2 | >2 and <=5 | 5 to 10
No of Tabs per report | <= 2 | 2 to 5 | > 5
#Prompts/runtime parameter | <=3 | >3 <= 5 | 6 to 10

## Estimator -3 (hidden)
Phase | Efforts | % Add On | Comments
Project Management | 3526.8517 | 10%
Analysis and Requirement Gathering | 1763.4259 | 5% | Concept Design | No req, only analysis
Design Efforts | 1587.0833 | 4.5% | Concept Design | Minimal efforts to mimic existing data models
Development and Unit Testing + 5% data migration | 19397.6844 | 55%
System(& Integration) Testing | 3632.6573 | 10.3% | Full load with history + Bug fixing | Will be majorly done by testing team with Auto Data validation Tool + 10% of critical reports performance testing efforts
Performance testing & data validation for 10% of critical reports + Data validation for all tables | 2715 | 7.7% | Based on Bottoms estimations from Testing Team
UAT | 1587.0833 | 4.5%
Deployment | 1058.0555 | 3% | CI-CD |  | 79.9724
KT & Hypercare | 0 | Based on schedule
Total Efforts | 35267.8413
[5 empty] | Complexity Matrix |  |  | Cut Estimates to Build & Test in Hrs |  |  | Total Efforts in PDs | % Savings (Reusability/ Tools/ Automations) | PD post Savings | Comments
BU | SL | Object Type | # Objects/ Jobs | Method of Migration | Simple | Mid | Complex | Simple | Mid | Complex
I&D | GCP | No. Of Tables / Files | 15724 | Mimic same logic using TD2BQ converter. Considered 60% simple 1 to 1 for data ingestion jobs | 60% | 30% | 10% | 0.5 | 1.5 | 2 | 1659.7556 | 70% | 497.9267 | Source to STG Simple jobs with Parameterized scripts 35% ; Transpiler & Universal Universal Migrator for Shema conversions 40% ;5% productivity with repeating task | 0.031667
I&D | GCP | # of Views, Semantic Layer | 25992 | Mimic same logic using TD2BQ converter | 50% | 40% | 10% | 1 | 2 | 3 | 4620.8 | 50% | 2310.4 | Transpiler & Universal Universal Migrator for Shema conversions 45% ;5% productivity with repeating task | 0.088889
I&D | GCP | # of ETL views with business Logic | 4052 | Mimic same logic using Google Data Pipelines & GBQs. | 30% | 40% | 30% | 8 | 12 | 18 | 5672.8 | 10% | 5105.52 | 5% savings with no requirements ; 2-3 % savings with parameterized common codes ; 1-3% from productivity from repeating tasks(e.g. CI-CD FM, Audit FM, Recon FM etc..) | 1.26
I&D | GCP | Informatica Transformation in GBQ SP | 2148 | Mimic same logic using Google Data Pipelines & GBQs | 30% | 40% | 30% | 8 | 16 | 24 | 3818.6667 | 10% | 3436.8 | 5% savings with no requirements ; 2-3 % savings with parameterized common codes ; 1-3% from productivity from repeating tasks(e.g. CI-CD FM, audit FM, Recon FM etc..) | 1.6
I&D | GCP | Stored Procedure Migration from TD to Big Query | 1005 | Mimic same logic using Google Data Pipelines & GBQs | 60% | 30% | 10% | 2 | 5 | 8 | 390.8333 | 50% | 195.4167 | Transpiler & Universal Universal Migrator for Shema conversions 45% ;5% productivity with repeating task | 0.19444
I&D | GCP | # TD to Sources (Oracle) Write-back Jobs | 394 | Mimic same logic using Google Data Pipelines & GBQs | 30% | 40% | 30% | 16 | 24 | 32 | 1050.6667 | 70% | 315.2 | Reused Access to Oracle scripts with retrofitting source connections with Big Query with same targets 60% ; 10% productivity with parameterizing connections | 0.8
I&D | GCP | # Cloud Storage buckets & archival Scripts | 50 | Same logic with minimal Retrofitting & change targets | 30% | 40% | 30% | 8 | 16 | 24 | 88.8889 | 70% | 26.6667 | Reused BIG Query to Oracle scripts with retrofitting source connections with Big Query with same targets 60% ; 10% productivity with parameterizing connections | 0.53333
I&D | GCP | RDM Cloud SQL Server to GBQ automated data refresh | 663 | Creation GCP Data Pipes with like to like functionality | 30% | 40% | 30% | 12 | 16 | 32 | 1443.8667 | 35% | 938.5133 | Reuse same population logic for Reference data uploads from files to STG with target connection changes and retrofitting with ~35% of savings | 1.4156
I&D | GCP | RDM UI Build | 1 | Create UI to enable business to upload reference data | 0% | 100% | 0% | 40 | 80 | 100 | 8.8889 | 0% | 8.8889 | Need to build with the same logic on new platform & new targets | 8.8889
I&D | GCP | Scheduling & Orchestration Scripts | 6039 | Mimic existing scheduler with Google Cloud Scheduler /Composer | 30% | 40% | 30% | 8 | 16 | 24 | 10736 | 50% | 5368 | Mimic same logic in Cloud Composer to achieve functionality ; reverse engineering with same logic with 30% savings; 10% savings with parametrizing simple jobs | 0.88889
I&D | Spot | # of Reports reporting efforts (SPOT fire) | 2484 | Change Source Connections & Minimal Retrofitting with smoke test | 30% | 40% | 30% | 2 | 4 | 6 | 1104 | 40% | 662.4 | Spotfire data connectors for at metadata level & replacing scripts with connection information will save ~30% savings; productivity with repeating tasks ~8-10% | 0.26667
I&D | BO | # of Reports reporting efforts (SAP BO) | 1039 | Change Source Connections & Minimal Retrofitting with smoke test | 50% | 30% | 20% | 2 | 3 | 4 | 311.7 | 10% | 280.53 | Metadata Extractor & replacing required changes in the meta codes ~8-10 % savings | 0.27
I&D | BO | # of Universe Reports reporting efforts (SAP BO) | 89 | Change Source Connections & Minimal Retrofitting with smoke test | 0% | 60% | 40% | 0 | 25 | 35 | 286.7778 | 40% | 172.0667 | Changing the connection @ Universe level & retrofitting common replacements using metadata extractor ~30% savings ; productivity with repeating tasks ~8-10% | 1.9333
I&D | Qlik/Tab | # of Reports reporting efforts (Tableau) | 8 | Change Source Connections & Minimal Retrofitting with smoke test | 30% | 40% | 30% | 2 | 4 | 6 | 3.5556 | 0% | 3.5556 |  | 0.44444
I&D | Qlik/Tab | # of Reports reporting efforts (QlikView) | 32 | Change Source Connections & Minimal Retrofitting with smoke test | 30% | 40% | 30% | 2 | 4 | 6 | 14.2222 | 0% | 14.2222 |  | 0.44444
I&D | Qlik/Tab | # of Reports reporting efforts (Composite) | 1 | Change Source Connections & Minimal Retrofitting with smoke test | 30% | 40% | 30% | 2 | 4 | 6 | 0.44444 | 0% | 0.44444 |  | 0.44444
I&D | Qlik/Tab | # of Reports reporting efforts (P&T) | 3 | Change Source Connections & Minimal Retrofitting with smoke test | 30% | 40% | 30% | 2 | 4 | 6 | 1.3333 | 0% | 1.3333 |  | 0.44444
I&D | GCP | API Integration Framework-Salesforce-Cast Iron | 230 | Same logic with minimal Retrofitting &retrofitting efforts for consumption | 30% | 40% | 30% | 1 | 3 | 8 | 99.6667 | 40% | 59.8 | Reuse same population logic from Access to Cast Iron Data Hub with replacing source & retrofit minor changes ~40 % savings | 0.26
I&D | BO | Move SAP BO on GCP with lift & Shift (Dev/Prod/QA) & Authentication | 0 | Lift & Shift on GCP Virtual Machines/ MP | 0% | 100% | 0% | 50 | 100 | 150 | 0 | 0% | 0 | Lift & Shift Platform Migration on GCP
I&D | Spot | Move Spotfire on GCP with lift & Shift (Dev/Prod/QA) & Authentication | 0 | Lift & Shift on GCP Virtual Machines/ MP | 0% | 100% | 0% | 50 | 100 | 150 | 0 | 0% | 0
I&D | Qlik/Tab | Move Tableau on GCP with lift & Shift (Dev/Prod/QA) & Authentication | 0 | Lift & Shift on GCP Virtual Machines/ MP | 0% | 100% | 0% | 50 | 100 | 150 | 0 | 0% | 0
I&D | Qlik/Tab | Move QlikView on GCP with lift & Shift (Dev/Prod/QA) & Authentication | 0 | Lift & Shift on GCP Virtual Machines/ MP | 0% | 100% | 0% | 50 | 100 | 150 | 0 | 0% | 0
I&D | GCP | Move Cast Iron (Sales Force) with lift & Shift (Dev/Prod/QA) & Authentication | 0 | Lift & Shift on GCP Virtual Machines/ MP | 0% | 100% | 0% | 50 | 100 | 150 | 0 | 0% | 0
[11 empty] | Without Savings | With Savings
[10 empty] | Man-days | 31312.8667 | 19397.6844
[11 empty] | % Savings | 38.05%

## Jobs by Layer (hidden)
|  | 60% | 40%
Objects | Counts | Ingestion | Data | Schema | Code | Layer | Comments
No. Of Tables / Files | 15724
No. Of Tables / Files STG 60% | 9434.4 | Yes | No | Yes | No | STG | No data migration for STG, Parameterized scripts for simple jobs for Source to STG
No. Of Tables / Files Core 25% | 3931 | No | Yes | Yes | No | Core | Schema & Data migration with 10% of data loads for history during Dev
No. Of Tables / Files Access 15% | 2358.6 | No | Yes | Yes | No | Access | Schema & Data migration with 10% of data loads for history during Dev
# of Views, Semantic Layer | 25992 | No | No | Yes | Yes | Access
# of ETL views with business Logic | 4052 | No | No | Yes | Yes | Core/ Access
Informatica Transformation in GBQ SP | 2148 | No | No | Yes | Yes | Core/ Access
Stored Procedure Migration from TD to Big Query | 1005 | No | No | Yes | Yes | Core/ Access
# TD to Sources (Oracle) Write-back Jobs | 394 | No | No | Yes | Yes | Access to Oracle
# Cloud Storage buckets & archival Scripts | 50 | No | No | Yes | Yes | Archive
RDM Cloud SQL Server to GBQ automated data refresh | 663 | No | No | Yes | Yes | Core/ Access
RDM UI Build | 1 | No | No | Yes | Yes | UI build
Scheduling & Orchestration Scripts | 6039 | No | No | No | No | Re-Write in Google Composer
API Integration Framework-Salesforce-Cast Iron | 230 | No | No | No | Yes | Access to Cast Iron

## Pivot (2) (hidden)
Sum of Total Efforts |  | Shore
Team | Role | India | US | (blank) | Grand Total
Architecture | Data Architect |  | 20 |  | 20
| Platform/Cloud Architect | 20 | 3.75 |  | 23.75
| Solution Architect | 21 |  |  | 21
Data Distillation 1 | Data Distillation Lead | 19 |  |  | 19
| Developer (GCP) | 54 |  |  | 54
| Developer (GCP)/ Tester | 102 |  |  | 102
Data Distillation 2 | Data Distillation Lead | 35 |  |  | 35
| Developer (GCP) | 51 |  |  | 51
| Developer (GCP)/ Tester | 99.5 |  |  | 99.5
Data Distillation 3 | Developer (GCP) | 48 |  |  | 48
| Developer (GCP)/ Tester | 93 |  |  | 93
Data Ingestion 1 | Data Ingestion Lead | 19.5 |  |  | 19.5
| Developer (GCP) | 16.5 |  |  | 16.5
| Developer (GCP)/ Tester | 77.5 |  |  | 77.5
Data Ingestion 2 | Data Ingestion Lead | 18 |  |  | 18
| Developer (GCP) | 15 |  |  | 15
| Developer (GCP)/ Tester | 71 |  |  | 71
Data Migration 1 | Data Migration Lead | 19.5 |  |  | 19.5
| Developer (GCP) |  | 19.5 |  | 19.5
| Developer (GCP)/ Tester | 53.5 |  |  | 53.5
Data Migration 1 | Developer (GCP) | 35.5 |  |  | 35.5
Data Migration 2 | Data Migration Lead | 18.5 |  |  | 18.5
| Developer (GCP) |  | 18.5 |  | 18.5
| Developer (GCP) | 34.5 |  |  | 34.5
| Developer (GCP)/ Tester | 50.5 |  |  | 50.5
Governance | Engagement Lead |  | 20.5 |  | 20.5
| Offshore Delivery Lead | 20.5 |  |  | 20.5
| Offshore Reporting Lead | 20 |  |  | 20
Platform & DevOps | DevOps SME | 18.5 |  |  | 18.5
| IDEA SME | 31 |  |  | 31
Quality Assurance | Jr Tesers | 55 |  |  | 55
| QA Lead |  | 19 |  | 19
| Sr Testers | 19 |  |  | 19
| Test Lead | 19 |  |  | 19
| Tester | 19 |  |  | 19
Report Repoint (Q/T) | Report Developer | 17 |  |  | 17
Report Repoint (SAP) | Report Developer | 38 |  |  | 38
| Report Developer / Tester | 51 |  |  | 51
Report Repoint (Tibco) | Report Developer | 38 |  |  | 38
| Report Developer / Tester | 69 |  |  | 69
Requrements | Data Analyst 1 |  | 20 |  | 20
| Data Analyst 2 | 19 |  |  | 19
| Data Analyst 3 | 20 |  |  | 20
| Lead Analyst |  | 19 |  | 19
Reverse Engineering | ETL SME (Inf + TD) |  | 16.5 |  | 16.5
| Informatica SME | 35 |  |  | 35
| Teradata SME | 19 |  |  | 19
Schema Migration | Developer (GCP) | 35.5 |  |  | 35.5
| Schema Migration Lead | 18.5 |  |  | 18.5
UI Development | UI Developer | 2.5 |  |  | 2.5
| UI/UX Designer | 2.5 |  |  | 2.5
(blank) | (blank) |  |  | 0 | 0
Grand Total |  | 1539 | 156.75 | 0 | 1695.75

## Sheet1 (hidden)
Row Labels | Sum of Total Efforts
Architecture | 1359.75 | 1359.75 | 3.818% | 8%
Data Distillation 1 | 3675 | 3675 | 10.32% | 30%
Data Distillation 2 | 3895.5 | 3895.5 | 10.94%
Data Distillation 3 | 2961 | 2961 | 8.315%
Data Ingestion 1 | 2383.5 | 2383.5 | 6.693% | 13%
Data Ingestion 2 | 2184 | 2184 | 6.133%
Data Migration 1 | 2688 | 2688 | 7.548% | 26%
Data Migration 2 | 2562 | 2562 | 7.194%
Governance | 1281 | 1281 | 3.597%
Platform & DevOps | 1039.5 | 1039.5 | 2.919% | 3%
Quality Assurance | 2751 | 2751 | 7.725% | 9%
Report Repoint (Q/T) | 357 | 357 | 1.003% | 13%
Report Repoint (SAP) | 1869 | 1869 | 5.248%
Report Repoint (Tibco) | 2247 | 2247 | 6.31%
Requrements | 1638 | 1638 | 4.6%
Reverse Engineering | 1480.5 | 1480.5 | 4.157%
Schema Migration | 1134 | 1134 | 3.184%
UI Development | 105 | 105 | 0.2949%
Grand Total | 35610.75

## Bayer current Rates (hidden)
[11 empty] | Cost |  |  | COR
[10 empty] | ADRC rate | 120 | 9 hrs |  | 120
| Q-Level | DE | US | Nearshore DE | Nearshore US | Offshore | China | Brazil |  |  | 13.3333 |  |  | 135
701.2924 | Q1 | 544 | 637 | 242 | 334 | 99 | 252 | 196 | 108.9921 |  | 106.6667 | 8 hrs
776.1556 | Q2 | 632 | 705 | 268 | 461 | 123 | 415 | 328 | 135.4144
877.4412 | Q3 | 771 | 797 | 343 | 512 | 157 | 515 | 599 | 172.846
985.3324 | Q4 | 903 | 895 | 472 | 769 | 213 | 709 | 819 | 234.4981
1204.4174 | Q5 | 1105 | 1094 | 657 | 922 | 264 | 1082 | 979 | 290.6455
| USD | 1.1009
| Current Rates | [8 empty] | Daily Hours | 8
| Q-Level |  | US |  |  | Offshore |  |  |  | Q-Level | DE | US | Nearshore DE | Nearshore US | Offshore | China | Brazil
| Q1 |  | 701.3 |  |  | 109 |  |  |  | Q1 | 0 | 87.6625 | 0 | 0 | 13.625 | 0 | 0
| Q2 |  | 776.16 |  |  | 135.42 |  |  |  | Q2 | 0 | 97.02 | 0 | 0 | 16.9275 | 0 | 0
| Q3 |  | 877.45 |  |  | 172.85 |  |  |  | Q3 | 0 | 109.6813 | 0 | 0 | 21.6062 | 0 | 0
| Q4 |  | 985.34 |  |  | 234.5 |  |  |  | Q4 | 0 | 123.1675 | 0 | 0 | 29.3125 | 0 | 0
| Q5 |  | 1204.42 |  |  | 290.65 |  |  |  | Q5 | 0 | 150.5525 | 0 | 0 | 36.3312 | 0 | 0
| P2W Rates |  | Onshore | % Delta |  | Offshore | % Delta
| Q1 |  | 648 | -7.6% |  | 189 | 73.39%
| Q2 |  | 752 | -3.113% |  | 225 | 66.15%
| Q3 |  | 920 | 4.849% |  | 261 | 51%
| Q4 |  | 888 | -9.879% |  | 279 | 18.98%
| Q5 |  | 1040 | -13.65% |  | 315 | 8.378%

## Old_PP & RL Plan (hidden)
May with small team
21
29043
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | [8 empty] | 20%
25%
[5 empty] | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
BU | SL | Role | Grade | Shore | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | Total PDs | Q Level | Current Daily Rate $ | Total Price | P2W Rates | Total Price as per P2W | ADRC Inc TRIO |  | USD ADRC Ex TRIO | Total Cost | GCP | Efforts | Loading | Delta
I&D | GCP | Engagment Manager | E1 | On | [23 empty] | 462 | Q5 | 1204.42 | 556442.04 | 1040 | 480480 | 1520 | 1216 | 1216 | 561792 |  | 24837.8598 | 24801 | 36.8598 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | GPC Data Architect | D2 | On | [23 empty] | 462 | Q5 | 1204.42 | 556442.04 | 1040 | 480480 | 1407.8053 | 1126.2443 | 1126.2443 | 520324.8491 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | BigQuery Data Analysts (With Tera Backgroud) | C1 | On | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 |  | 1281 | Q2 | 776.16 | 994260.96 | 752 | 963312 | 1017.3831 | 813.9065 | 813.9065 | 1042614.2219
I&D | GCP | GCP Platform Architect | C2 | On | [23 empty] | 462 | Q3 | 877.45 | 405381.9 | 920 | 425040 | 1017.3831 | 813.9065 | 813.9065 | 376024.8013 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | SQL SMEs (with Teradata background) | C2 | On | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  | 861 | Q3 | 877.45 | 755484.45 | 920 | 792120 | 1017.3831 | 813.9065 | 813.9065 | 700773.4934
Testing BU | Tera | Testing Lead | C2 | On | [23 empty] | 462 | Q3 | 877.45 | 405381.9 | 920 | 425040 | 800.515 | 800.515 | 800.515 | 369837.9387 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | Program Manager/Delivery Lead | D2 | Off | [23 empty] | 462 | Q5 | 290.65 | 134280.3 | 315 | 145530 | 227.46 | 170.595 | 187.8132 | 86769.6768 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | Lead GCP Data Architect | D1 | Off | [23 empty] | 462 | Q4 | 234.5 | 108339 | 279 | 128898 | 198.12 | 148.59 | 163.5872 | 75577.2812 |  |  |  |  | 1522574.334 | 118812.2376 | 3503735.8788 | 379153.9883 | 5524276.4386 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | GCP Data Engineer Lead(s) | C2 | Off |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  | 1239 | Q3 | 172.85 | 214161.15 | 261 | 323379 | 161.85 | 121.3875 | 133.6391 | 165578.8949 |  |  |  |  | 1641386.5716 |  | 3882889.867
I&D | GCP | GCP Sr Data Engineer(s) | C1 | Off |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 |  | 1596 | Q2 | 135.42 | 216130.32 | 225 | 359100 | 118.66 | 88.995 | 97.9773 | 156371.7155 | [8 empty] | 1741386.5716
I&D | GCP | GCP Data Engineer (s) | B2 | Off |  |  | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 |  | 3171 | Q2 | 135.42 | 429416.82 | 225 | 713475 | 80.52 | 60.39 | 66.4852 | 210824.4509 |  |  |  |  | Onshore | Offshore |  |  | 4282889.867
I&D | GCP | GCP Data Engineer(s) | B1 | Off |  |  | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 |  | 3990 | Q1 | 109 | 434910 | 189 | 754110 | 62.56 | 46.92 | 51.6556 | 206105.986 |  |  |  |  | 400000 | 100000 | 500000 |  | 6024276.4386
I&D | GCP | GCP Data Engineer/Testerer(s) | B1 | Off |  |  | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 5 |  | 3612 | Q1 | 109 | 393708 | 189 | 682668 | 62.56 | 46.92 | 51.6556 | 186580.1558 |  |  |  |  | Travel | Misc |  |  | 10040460.7311
I&D | GCP | GCP Data Engineer/Testerer (s) | A5 | Off |  |  | 8 | 8 | 10 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 7 |  | 5481 | Q1 | 109 | 597429 | 189 | 1035909 | 34.04 | 25.53 | 28.1067 | 154053.0578 |  |  |  |  | 18181.8182 | 4545.4545 |  |  | 10843697.5895
I&D | GCP | SQL SMEs (with Teradata background) | B2 | Off | [23 empty] | 420 | Q2 | 135.42 | 56876.4 | 225 | 94500 | 80.52 | 60.39 | 66.4852 | 27923.7683 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | GCP DE (with Infomatica Background) | B2 | Off | [23 empty] | 420 | Q2 | 135.42 | 56876.4 | 225 | 94500 | 80.52 | 60.39 | 66.4852 | 27923.7683 | bar: 2022-05-01 to 2024-02-01
I&D | GCP | GCP DE (with Infomatica Background) | B1 | Off | [23 empty] | 420 | Q1 | 109 | 45780 | 189 | 79380 | 62.56 | 46.92 | 51.6556 | 21695.367 | bar: 2022-05-01 to 2024-02-01
I&D | SAP BO | Sr. BO Developer | C1 | Off | [23 empty] | 273 | Q2 | 135.42 | 36969.66 | 225 | 61425 | 118.66 | 88.995 | 97.9773 | 26747.7934 | SAP BO | Efforts | Loading | Delta | bar: 2022-05-01 to 2024-02-01
I&D | SAP BO | Jr. BO Developer | B2 | Off | [23 empty] | 336 | Q2 | 135.42 | 45501.12 | 225 | 75600 | 80.52 | 60.39 | 66.4852 | 22339.0147 |  | 615.5315 | 609 | 6.5315 | bar: 2022-05-01 to 2024-02-01
I&D | Rep & Viz | Sr SpotFire/Qlik/Tab SME | C1 | Off | [23 empty] | 252 | Q2 | 135.42 | 34125.84 | 225 | 56700 | 118.66 | 88.995 | 97.9773 | 24690.2709 | SP/Tab/Qlik | Efforts | Loading | Delta | bar: 2022-05-01 to 2024-02-01
I&D | Rep & Viz | Spotfire /QlikSME | B2 | Off | [23 empty] | 378 | Q2 | 135.42 | 51188.76 | 225 | 85050 | 80.52 | 60.39 | 66.4852 | 25131.3915 |  | 927.4596 | 924 | 3.4596 | bar: 2022-05-01 to 2024-02-01
I&D | Rep & Viz | Jr SpotFire/Tableu SME | B1 | Off | [23 empty] | 294 | Q1 | 109 | 32046 | 189 | 55566 | 62.56 | 46.92 | 51.6556 | 15186.7569 | bar: 2022-05-01 to 2024-02-01
Testing BU | Testing | Test Lead | C1 | Off | [23 empty] | 378 | Q2 | 135.42 | 51188.76 | 225 | 85050 | 84 | 84 | 84 | 31752 | Testing | Efforts | Loading | Delta | bar: 2022-05-01 to 2024-02-01
Testing BU | Testing | Sr Testers & Data / Report validators | B2 | Off | [23 empty] | 378 | Q2 | 135.42 | 51188.76 | 225 | 85050 | 63 | 63 | 63 | 23814 |  | 2715 | 2709 | 6 | bar: 2022-05-01 to 2024-02-01
Testing BU | Testing | Tester & Data / Report validators | B1 | Off | [23 empty] | 378 | Q1 | 109 | 41202 | 189 | 71442 | 46 | 46 | 46 | 17388 | bar: 2022-05-01 to 2024-02-01
Testing BU | Testing | Jr Tesers & Data / Report validators | A5 | Off |  |  |  |  | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 |  |  | 1113 | Q1 | 109 | 121317 | 189 | 210357 | 35 | 35 | 35 | 38955
[5 empty] | 189 | 189 | 987 | 1155 | 1344 | 1470 | 1554 | 1554 | 1575 | 1575 | 1575 | 1554 | 1554 | 1554 | 1554 | 1554 | 1533 | 1512 | 1512 | 1386 | 1323 | 840 |  | 29043 | 0 |  | 6826028.58 |  | 8764161 |  |  |  | 5116775.6544
|  | 10872146.3093 |  |  | 0.6508% | 0.6508% | 3.398% | 3.977% | 4.628% | 5.061% | 5.351% | 5.351% | 5.423% | 5.423% | 5.423% | 5.351% | 5.351% | 5.351% | 5.351% | 5.351% | 5.278% | 5.206% | 5.206% | 4.772% | 4.555% | 2.892% |  | 31366.44 |  |  | 5431917.314 |  | 5431917.314
[5 empty] | 70751.4944 | 70751.4944 | 369480.0264 | 432370.2437 | 503121.7381 | 550289.401 | 581734.5097 | 581734.5097 | 589595.7868 | 589595.7868 | 589595.7868 | 581734.5097 | 581734.5097 | 581734.5097 | 581734.5097 | 581734.5097 | 573873.2325 | 566011.9554 | 566011.9554 | 518844.2924 | 495260.4609 | 314451.0863 | 0 |  |  |  | 20.42% |  | 38.02%
[5 empty] | 0.6508% | 0.6508% | 3.398% | 3.977% | 4.628% | 5.061% | 5.351% | 5.351% | 5.423% | 5.423% | 5.423% | 5.351% | 5.351% | 5.351% | 5.351% | 5.351% | 5.278% | 5.206% | 5.206% | 4.772% | 4.555% | 2.892% |  | 2247 | 462
[6 empty] | Grades | % Allocation
[5 empty] | 2022-05-01: Q5; 2022-06-01: E1; 2022-07-01: 1.591%; 2022-08-01: Q5; 2023-04-01: 7057449 |  | ON |  | Off
[5 empty] | 2022-05-01: Q5; 2022-06-01: D2; 2022-07-01: 3.181%; 2022-08-01: Q5; 2023-03-01: Contingency; 2023-04-01: 7622044.92 | 0 | Q1 | 0 | Q1 | 15288 | 0.61023
[5 empty] | 2022-05-01: Q4; 2022-06-01: D1; 2022-07-01: 1.591%; 2022-08-01: Q4; 2023-10-01: 480 | 0.32105 | Q2 | 1281 | Q2 | 7602 | 0.30344
[5 empty] | 2022-05-01: Q3; 2022-06-01: C2; 2022-07-01: 10.41%; 2022-08-01: Q3; 2023-10-01: 13940640; 2023-11-01: 15055891.2 | 0.44737 | Q3 | 1785 | Q3 | 1239 | 0.049455
[5 empty] | 2022-05-01: Q2; 2022-06-01: C1; 2022-07-01: 13.02%; 2022-08-01: Q2; 2023-10-01: 5431917.314; 2023-11-01: 5431917.314 | 0 | Q4 | 0 | Q4 | 462 | 0.018441
[5 empty] | 2022-05-01: Q2; 2022-06-01: B2; 2022-07-01: 17.57%; 2022-08-01: Q2; 2023-11-01: 0.63922 | 0.23158 | Q5 | 924 | Q5 | 462 | 0.018441
[5 empty] | 2022-05-01: Q1; 2022-06-01: B1; 2022-07-01: 29.93%; 2022-08-01: Q1; 2023-10-01: 9053195.5234 |  |  | 3990 |  | 25053
[5 empty] | 2022-05-01: Q1; 2022-06-01: A5; 2022-07-01: 22.7%; 2022-08-01: Q1; 2023-10-01: 288.6268 |  |  |  |  | 29043 | 31366.44
[29 empty] | 4309.2 |  | 27057.24
[5 empty] | 2022-06-01: On/Off; 2022-07-01: 13.74% |  |  | 31366.44
[5 empty] | 2022-12-01: 74 |  |  | 10872146.3093
[5 empty] | 2022-12-01: 10.1663 |  |  | 346.6172
43.3271

## Important Links (hidden)
https://cloud.google.com/bigquery-transfer/docs/data-warehouse-migration-overview |  |  |  | BigQuery Data Transfer Service
https://www.youtube.com/watch?v=lc68XluDeH4 |  |  |  | Special migration agent
https://cloud.google.com/bigquery-transfer/docs/teradata-migration
| Foundation |  | Network
Environment
IAM
Cloud Build Teraform
Souce Repo
Cloud DNS
Partner Interconnect
Cloud Operations Suite
Automated TD2BQ transfer agent
Pelican
DataSet | Schema | `--> Location

## TOC (hidden)
PPT Response
Slide # | Sub Chapter | Owner | Contributor | Reviewers
1 | Company stats (I&D & GCP capabilities)
2 | Understanding your objectives & Value Proposition
3 | Current V/s Proposed Solution Architecture & merits
4 | Our Data ,Schema, Code Migration Strategy
5 | Target System Migration Strategy | CIS |  |  | Spot, SAP BO, Tableau, SF,Talend,SAP IBP, Altryx
6 | Proposed End to End GCP Architecture
7 | Our high level testing strategy to gain data trust on migration
8 | Proposed implementation timelines
9 | Tools & Accelerators to expedite migration process
10 | Possible risks & mitigation plans
11 | Pricing & Commercials
12 | Key Assumptions
13 | Fit Gap Analysis & Due Diligence Approach
14 | Case Studies with successful migration done in the past
15 | Case Studies with successful migration done in the past

## Questions & Clarifications (hidden)
Sr# | Questions | Clarifications by Bayer
1 | Can you specify version of Teradata used on premise.?
2 | How data from Stage to Core & finally to Access layer is being propagated currently .? Are you using Informatica or BTEQ scripts for the same.?
3 | What is your preferred data repository in GCP i.e. Snowflake, Google Big Query.?
4 | What existing services are up & running on current GCP platform you may want to leverage in this program.?
5 | Is it safe to assume 3rd party target system owners i.e. Cast Iron (Sales Force, ADW) will retrofit small changes as needed in their systems post migration.?
6 | Since Bayer already have subscription for GCP is it safe to assume cost for licensing, hosting and support will be borne by Bayer.?
7 | Can we know how we need to design waves in the high level project timelines.? Can you provide us with high level inputs to logically group supplied volumetrics in to the waves.?
8 | Can you able to clarify, what are expected services for retiring Teradata EDW platform from the supplier.?
9 | What would be the scope of migration for down stream Cast Iron (Salesforce) & ADW migration, do these systems to be migrated on GCP, if so, can you please elaborate detail scope .?
10 | Scope of Informatica is to limited to orchestrate data load with Tera Data Stored SQLs in BTEQ scripts only.? Or otherwise please specify how Informatica is leveraged currently.?
11 | Please specify Informatica version used currently.?
12 | Is it safe to assume all existing ETL interfaces & reports should be re-used with minimal retrofication for this program with repointing to the GCP environment as is.?
13 | Can you able to elaborate what P&T APIs stands for..? what would be the technology platform & scope of services.?
14 | Cloud Storage buckets & archival Scripts are written in which programming language.?
15 | Can you able to specify which technology used for scheduling & orchestration currently.?
16 | Can you able to specify what is used authentication mechanism is implemented to access all downstream applications in the scope.? i.e. Active Directory, SSO, LDAP etc..?
17 | Can you able to specify how many tables/entities are available in access layer.?